## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | Unable to login with correct username and password | The website does not allow to login even with the correct username and passwords | UC01 | High | Nhan | 2021-02-08 | Closed | Fixed by Kim
B002 | Still able to login with incorrect username and password | The website still admits for user to access the home page although username or password is incorrect | UC01 | High | Kim | 2021-02-08 | Closed | Fixed by Kim
B003 | Login with number username and password | The website still admits for user to access to home page although username or password only has whole number | UC01 | Medium | Phuoc | 2021-03-08 | Closed | Fixed by Kim
B004 | Adding multiple values to quantity when scanning the QRCode | The quantity should be increased by 1 every time when 1 product is scanned, but in this case, quantity was increased more than 1 | UC02 | High | Long | 2021-04-08 | Closed | Fixed by Long
B005 | Able to click the "Sell" button when there is no item | The "Sell" button should be disabled while there is no added product | UC02 | Low | Phuoc | 2021-05-08 | Closed | Fixed by Long
B006 | Sending receipts to customers' email addresses | A e-receipt shoud be sent to the customer's email address but nothing was sent | UC02 | Low | Nhan | 2021-05-08 | Open | Long should take a look at the function corresponding to the 'send' button at Home page
B007 | Item doesn't show up in the table after scanning QRCode | The right item should be added to the table when it's QRCode is scanned but nothing was shown | UC02 | High | Kim | 2021-05-08 | Closed | Fixed by Long
B008 | Item doesn't show up in the table after adding data manually | The item should be added to the table after inputing it's id to the box below the QRBox, but nothing was shown in the table | UC02 | Medium | Long | 2021-06-08 | Open | Kim should check the home page again especially the function of 'add' button and product table
B009 | Transaction list did not sort transactions by ascending time | The order of the transactions should be printed following latest time but transaction list still shows the order of transactions corresponding to the order of ascending transactions' id | UC03 | Medium | Kim | 2021-08-08 | Closed | Fixed by Phuoc
B010 | The position of the transaction table is glitched | The table is in the wrong position, it should be in the middle of the page, but this case, the botton of table override the navigation bar leaving a lot of blank space at the bottom | UC03 | Low | Phuoc | 2021-08-08 | Closed | Fixed by Phuoc
B011 | Transaction's status did not change after clicking edit | The transaction's status should be changed when it's edited but nothing was shown according to changes | UC03 | Medium | Long | 2021-08-08 | Closed | Fixed by Nhan
B012 | The arrow button's behavior is not correct | The arrow button should show the previous or the next page. But it's able to click on the previous button while the first page is displayed, the same happens to the last page. | UC03 | Medium | Nhan | 2021-09-08 | Closed | Fixed by Nhan
B013 | The redirect page after clicking the arrow buttons | The button is glitched. After clicking the next button, the next page is shown but immediately redirects back to the first page that the user see | UC03 | Medium | Kim | 2021-09-08 | Closed | Fixed by Nhan
B014 | Nothing was shown after adding new item to store | A pop up should be displayed the status of that the adding process (fail or success), but nothing was shown | UC04 | Low | Phuoc | 2021-10-08 | Open | Phuoc should check the database as well as the CSS file
B015 | The view detail button is not working properly | The view detail should show a picture of the product along side with it's detail, these will be display on a pop up which will dim and blur the background. In this case, nothing happens when clicking the button | UC04 | Low | Long | 2021-10-08 | Open | Nhan should check the function of the button